## Cover
HANOI UNIVERSITY OF SCIENCE AND TECHNOLOGY
School of Information and communications technology
Test Plan
Version 1.0
AIMS PROJECT
Subject: Software Development
Bui Tran Hai Quan
20194821
Hanoi, December, 2022

## Table of Contents
Table of Contents
1 | Instructions
2 | Overall Description
3 | Testing Approach Strategy
4 | Unit Testing Summary
5 | Test Case Details

## Introduction
1. Introduction
1.1. Objective
(1) Purpose: - Identify basic information about the project and functional components to be tested and not tested - List the requirements for the test (Test Requirements) - Devising a testing strategy (Test Approach) - Estimate resource requirements and costs for testing - Documents to be prepared after completion of testing (2)Level: Specific Test Plan for Testing PlaceOrder/RushOrder Controller
1.2 Scope
(1) This Test Plan is designed for the AIMS Project (2) AIMS Project is an E-commerce system specialized in buying and selling media products. (3) This Level Test Plan is intended to meet an important part of the project's requirements, including PlaceOrder Usecase and PlaceRushOrder Usecase: - Place Order UC: Validating customer's phone number, address of the customer and customer's name. (For PlaceOrderController) - Place Rush Order UC: Validating supported address and supported media, changing Formula of calculating shipping fees. (For PlaceRushOrdercontroller) (4) This Level Test Plan is a part of The Master Plan: AIMS project version 1.0
1.3. Glossary
Terms | Definition
AIMS | An Internet Media Store
Black-box Testing | A testing strategy in Software Development
White-box Tesitng | A testing strategy in Software Development
Unit Test | A level of Testing
1.4. References
Centers for Medicare & Medicaid Services. (n.d.). Test Case Specification. Retrieved from Centers for Medicare & Medicaid Services: https://www.cms.gov/Research-Statistics-Data-and-Systems/CMS-Information-Technology/XLC/Downloads/TestCaseSpecification.docx Centers for Medicare & Medicaid Services. (n.d.). Test Plan. Retrieved from Centers for Medicare & Medicaid Services: https://www.cms.gov/Research-Statistics-Data-and-Systems/CMS-Information-Technology/XLC/Downloads/TestPlan.docx guru99. (n.d.). Download Sample Test Case Template: Example Excel, Word Formats. Retrieved from guru99: https://www.guru99.com/download-sample-test-case-template-with-explanation-of-important-fields.html Master Test Plan: AIMS project v1.0

## Overall Description
2. Overall Description
2.1. General Overview
(1) Place Order Usecase: describes the interaction between customers and AIMS software when the customer wishes to place an order. - Referenced documentation: Use case specification - Place Order, Activity Diagram - Place Order, Sequence Diagram - Place Order, Communication diagram - Place Order, Class Diagram - Place Order (2) Place Rush Order Usecase: describes the interaction between customers and AIMS software when the customer wishes to place an rush order. - Referenced documentation: Use case specification - Place Rush Order, Activity Diagram - Place Rush Order, Sequence Diagram - Place Rush Order, Communication diagram - Place Rush Order, Class Diagram - Place Rush Order (3) For more information and understanding, these documents are refered: Usecase Diagram, AIMS detailed package diagram, AIMS detailed class diagram, General class diagram
2.2. Assumptions/Constraints/Risks
2.2.1. Assumptions
In the simulator, for simplicity, customers do not need an account to place orders and pay orders. The software has no feature allowing customers to sign up and sign in. For our simulated system, in terms of payment method, each group will be issued a virtual credit card with the information. To perform operations with a credit card, the AIMS Software will call a number of available APIs.
2.2.2. Constraints
***Environment needs: (1)Hardware: Personal computer having Java: CPU RAM HDD Architecture Intel Core i5, 2.3GHz 4 GB 360 GB 64bit (2) Software: - Eclipse IDE installing JUnit ***User's Environment: Personal computer: CPU RAM HDD Architecture Intel Core i5, 2.3GHz 4 GB 360 GB 64bit
2.2.3. Risks
(1)Risks - Team member lacks necessary skills for testing. - Project schedule is too tight - Test Manager has poor management skills - Lack of cooperation negatively affects member productivity - Wrong budgeting and cost overruns (2) Contingencies: - Plan a training course to improve the skills of the members - Set Test Priority for each test activity. - Make a training plan for the manager - Encourage each team member to perform their duties and inspire them to put in more effort. -Set scope before starting work, pay a lot of attention to project planning and continuously monitor and measure progress

## Testing Approach Strategy
3. Testing Approach/Strategy
(3.1) Unit Test - Executed by development team - Use both White-box and Black-box Testing Strategy - Supported by Junit (3.2) System Testing - Only executed test cases on PC - Use more tools to support interface testing - Black-box Testing Strategy

## Unit Testing Summary
4. Unit Testing Summary
4.1. Traceability from Test Cases to Use Cases
<Mark the cell with an "x" where the Test Case tests.>
USE CASE ID |  |  | UC001 | UC002 | UC003 | UC004 | UC005 | …
Test Case ID | Test CaseTitle | Totals | 2 | 1 | 2 | 0 | 1 | 1
TC001 |  | 1 | x
TC002 |  | 3 | x | x | x
TC006 |  | 1 |  |  |  |  | x
TC007 |  | 1 | [5 empty] | x
… |  | 1 |  |  | x
Table: Test Case-to-Use Case Traceability Matrix
4.1.1. Test Suite for UC002-"Use Case Name"
Test Suite ID | Test Suite Title | Description |  |  | Test Cases
TS001 | <Test Suite Title> | <Briefly describe the test suite> |  |  | <Test Case ID, Test Case ID>
4.2. Traceability from Test Cases to Requirements
<Mark the cell with an "x" where the Test Case tests.>
REQUIREMENT ID |  |  | RQ001 | RQ002 | RQ003 | RQ004 | RQ005 | …
Test Case ID | Test CaseTitle | Totals | 1 | 1 | 1 | 0 | 1 | 1
TC001 |  | 1 | x
TC002 |  | 3 |  | x | x |  | x
TC003 |  | 1 | x
TC004 |  | 1 |  | x
TC005 |  | 2 |  |  |  |  | x | x
… |  | 1 |  |  | x
Table: Test Case-to-Requirement Traceability Matrix
4.2.1. Test Suite for RQ001-"Requirement Title"
Test Suite ID | Test Suite Title | Description |  |  | Test Cases
TS004 | <Test Suite Title> | <Briefly describe the test suite> |  |  | <Test Case ID, Test Case ID>

## Test Case Details
5. Test Case Details
5.1. Test Case Specification for "Place Order"
Test Case ID |  | TC001 | Test Case Description | Test the UC Place Order
Created By |  | Hoang Van Tien | Reviewed By | Hoang Van Tien | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Hoang Van Tien | Date Tested | 2022-12-10 | Test Case (Pass, Fail, Not Executed) |  | Pass
# | Prerequisites:
1 | Access to AIMS Software
2
# | Test Data |  | Value
1 | Quantity |  | 100
2 | Update quantity |  | 7
3 | Name |  | VanTien
4 | Phone |  | 876477922
5 | Province/City |  | Hanoi
6 | Address |  | 1 DaiCoViet, HaiBaTrung District, Hanoi City
7 | Shipping Instruction |  | Delivery from 11.00 AM to 6.00 PM
8 | Payment Method |  | CreditCard
9 | Card Number |  | 19273876254
10 | Card Holder Name |  | Hoang Tien
11 | Expiration Date |  | 2023-12-12
12 | Card Security Code |  | 1243
Test Scenario |  | Verify if customer can place an order
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | View the cart |  | Cart should open | As Expected | Pass
2 | The software displays the info of the cart (subtotal, VAT,…) |  | Screen must display clearly | As Expected | Pass
3 | Request to place an order |  | Success to request | As Expected | Pass
4 | Update delivery info and instruction |  | Update successfully | As Expected | Pass
5 | The software displays the invoice |  | Screen must display clearly | As Expected | Pass
6 | Confirm invoice |  | Confirm successfully | As Expected | Pass
7 | Provide Payment Method |  | Payment method: Credit Card successfully | As Expected | Pass
8 | Provide Transaction info |  | Record transaction info done | As Expected | Pass
9 | Software sends an email of invoice and transaction |  | Send successfully | As Expected | Pass
10 | Order approval |  | Admin approves successfully | Not Expected | Fail
5.2. Test Case Specification for "Place Rush Order"
Test Case ID |  | TC002 | Test Case Description | Test the UC Place Rush Order (extends from UC Place Order)
Created By |  | Hoang Tien | Reviewed By | Hoang Tien | Version | 1.0
QA Tester’s Log |  | Review comments from Reviewer incorprate in version 1.0
Tester's Name |  | Hoang Van Tien | Date Tested | 2022-12-10 | Test Case (Pass, Fail, Not Executed) |  | Pass
# | Prerequisites:
1 | Access to AIMS Software and already be in delivery form step of Place Order UC.
# | Test Data |  | Value
1
Test Scenario |  | Verify if customer can palce an rush order
Step # | Step Details |  | Expected Results | Actual Results | Pass / Fail / Not executed / Suspended
1 | Choose to place rush order |  | Place rush order successfully | As Expected | Pass
2 | Submit delivery form |  | Submit successfully | As Expected | Pass
3 | Validate the input |  | Validate correctly | As Expected | Pass
4 | Software checks if there is media and the shipping address are supported |  | Verify correctly | As Expected | Pass
5 | Software displays the screen for rush order, allowing the customer to update rush order info |  | Display clearly and able to update | As Expected | Pass
6 | Software changes the formula to calculate shipping fees |  | Change successfully | As Expected | Pass
7 | Continue to calculating shipping fees steps |  | Switch to step successfully | Not Expected | Fail